## Sprint 1
Sprint 1
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw ERD | Draw ERD | DungNT | Processing | 10 | 0 | 0 | 0 | 0 | 0
Draw Overview Usecase Diagram | Draw Usecase diagram | DungNT | Processing | 0 | 0 | 0 | 0 | 0 | 0
Design UI mockup | Design Homepage | DongHN | Done | 0 | 0 | 0 | 0 | 0 | 0
| Design View Requests Page | DongHN | Done | 0 | 0 | 0 | 0 | 0 | 0
| Design Admin Page | MinhLN | Processing | 0 | 0 | 0 | 0 | 0 | 0
| Design Profile User Page | MinhLN | Processing | 0 | 0 | 0 | 0 | 0 | 0
| Design Change Password Page | MinhLN | Processing | 0 | 0 | 0 | 0 | 0 | 0
| Design Create Request Page | LocHV | Processing | 0 | 0 | 0 | 0 | 0 | 0
| Design View New User Page | MinhLN | Processing | 0 | 0 | 0 | 0 | 0 | 0
| Design View Detail Request Page | LocHV | Processing | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Report 1 | Introduction, current situation | DungNT | Done | 3 | 1 | 2 | 0 | 0 | 0
| Problem definition | LocHV | Done | 5 | 3 | 1 | 1 | 0 | 0
| Proposed solution | LocHV | Done | 5 | 3 | 1 | 1 | 0 | 0
| Functional requirement, role responsibility | DungNT | Done | 4 | 1 | 2 | 1 | 0 | 0
| Total |  |  | 27 | 8 | 6 | 3 | 0 | 0

## Sprint 2
Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | - Usecase diagram | ViNTT | Done | 4 | 0 | 0 | 0 | 0 | 0
| - ERD diagram | ViNTT | Done | 6 | 2 | 0 | 0 | 0 | 0
| - Report 1 | ViNTT | Done | 6 | 6 | 0 | 0 | 0 | 0
| - Trie Tree Data Structure - Research | ViNTT | Done | 10 | 10 | 10 | 10 | 3 | 0
| - SpringBoot, JPA, Hibernate - Conceptual Learning | ViNTT | Done | 2 | 2 | 2 | 0 | 0 | 0
|  | TruongLN | Done | 10 | 4 | 0 | 0 | 0 | 0
|  | AnhTP | Done | 13 | 7 | 3 | 0 | 0 | 0
|  | TrinhND | Done | 13 | 7 | 3 | 0 | 0 | 0
| - React JS (State vs. Prototype) - Trainning | TruongLN | Done | 10 | 8 | 4 | 0 | 0 | 0
| - React JS (State vs. Prototype) - Learning | ViNTT | Done | 2 | 2 | 2 | 0 | 0 | 0
|  | AnhTP | Done | 13 | 11 | 7 | 2 | 0 | 0
|  | TrinhND | Done | 13 | 11 | 7 | 2 | 0 | 0
| - Set up & Configure Source Structure | TruongLN | Done | 12 | 12 | 12 | 8 | 0 | 0
Implement UI to Prototype | - Implement UI Login Page | AnhTP | Done | 10 | 10 | 10 | 10 | 4 | 0
| - Implement UI Register page | TrinhND | Done | 10 | 10 | 10 | 10 | 4 | 0
Report 2 | Problem Definition | AnhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| Future Plans | TrinhND | Done | 4 | 4 | 4 | 4 | 4 | 0
| Development Environment | TruongLN | Done | 8 | 8 | 8 | 8 | 8 | 0
| Project Organization | ViNTT | Done | 5 | 5 | 5 | 1 | 0 | 0
| Project Management Plan | ViNTT | Done | 5 | 5 | 5 | 5 | 1 | 0
| Total |  |  | 160 | 128 | 96 | 64 | 28 | 0

## Sprint 3
Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Update ERD | ViNTT | Done | 4 | 2 | 0 | 0 | 0 | 0
Research + Training + Learning | - Trie Tree Data Structure Implement | ViNTT | Done | 18 | 12 | 6 | 2 | 0 | 0
| - Graph with Adjacency List Learning | ViNTT | Done | 6 | 6 | 6 | 6 | 0 | 0
| - Queue in Java Revising | ViNTT | Done | 4 | 4 | 4 | 0 | 0 | 0
| - Implement Sitemap | ViNTT | Done | 8 | 8 | 8 | 8 | 8 | 0
| - React JS (Route) - Trainning | TruongLN | Done | 8 | 0 | 0 | 0 | 0 | 0
| - React JS (Route) - Learning | AnhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
|  | TrinhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
Research + write doc | - Sitemap Research | AnhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
| - Speed Test basic | TrinhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| - Page Test basic | AnhTP | Done | 2 | 2 | 2 | 2 | 2 | 0
| - Redirection Test basic | AnhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
Implement UI to Prototype | - Implement Landing page | TruongLN | Done | 4 | 4 | 0 | 0 | 0 | 0
| - Implement Spelling test page | TrinhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
| - Implement Grammar test page | AnhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
| - Implement Broken links test page | TrinhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
| - Implement Broken pages test page | TrinhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
| - Implement Missing files test page | TrinhTP | Done | 4 | 4 | 4 | 4 | 0 | 0
| - Implement Prohibited content test page | AnhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
| - Implement Mobile layout test page | TrinhTP | Done | 4 | 4 | 4 | 4 | 0 | 0
| - Implement Speed test page | TrinhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| - Implement JavaScript errors test page | AnhTP | Done | 4 | 4 | 4 | 0 | 0 | 0
| - Implement Favicons test page | TrinhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| - Implement Cookie law test page | AnhTP | Done | 4 | 4 | 4 | 0 | 0 | 0
| - Implement Server behavior test page | TrinhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| - Implement Pages test page | AnhTP | Done | 2 | 2 | 2 | 2 | 0 | 0
| - Implement Contact details test page | AnhTP | Done | 4 | 4 | 4 | 4 | 0 | 0
| - Implement Redirections test page | AnhTP | Done | 4 | 4 | 4 | 4 | 2 | 0
| - Implement Admin page: Manage Websites | TruongLN | Done | 8 | 8 | 8 | 0 | 0 | 0
| - Implement Admin page: Manage Staff Accounts | TruongLN | Done | 8 | 8 | 8 | 8 | 0 | 0
| - Implement Admin page: Manage Word List | TruongLN | Done | 8 | 8 | 8 | 8 | 8 | 0
Implement Base Component | - Implement Login function | TruongLN | Done | 4 | 4 | 0 | 0 | 0 | 0
| Total |  |  | 160 | 128 | 96 | 72 | 40 | 0

## Sprint 4
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Research + Learning | Selenium, Jsoup Research | ViNTT | Done | 2 | 0
|  | AnhTP | Done | 8 | 0
| PhantomJS Research | TrinhND | Done | 8 | 0
Implement features of Staff role | Implement TrieTree for Missing Letter Case | ViNTT | On-going | 8 | 4 | 0
| Implement function: Contact test | ViNTT |  | 5
|  | AnhTP |  | 8
| Implement function: Page Test | ViNTT | On-going | 5
|  | AnhTP | On-going | 8
| Implement function: Speed test | TruongLN | On-going | 20 | 12 | 4
|  | TrinhND | On-going | 10 | 10 | 4
| Implement function: JavaScript Error test | TruongLN |  | 20
|  | TrinhND |  | 14
Design Diagram | Update Physical Diagram | ViNTT |  | 6 | 4
| Design Dictionary Database | VinTT |  | 8 | 8 | 4
| Design System Database | ViNTT |  | 6
Report 3 | Usecase specification | TrinhND |  | 8 | 8 | 6
|  | AnhTP |  | 16
| Total |  |  | 160